## 0.16
Repository | Title | Assignees | Reviewers | Linked pull requests | Status | Priority | Labels | Milestone | Status Details | Is represented on board by a PR? | Reviewers To Exclude | Iteration | Status Date
| ⬇️⬇️⬇️ Todo: Gateway Items ⬇️⬇️⬇️ |  |  |  | 🥞 Todo | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-06-14
| ⬇️⬇️⬇️ Todo: Other Initiatives ⬇️⬇️⬇️ |  |  |  | 🥞 Todo | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-06-14
| Bitswap issue |  |  |  | 🥞 Todo | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-08
ipfs/kubo | Improve resource manager UX |  |  |  | 🥞 Todo | undefined | kind/enhancement | kubo 0.15 | undefined | undefined | undefined | kubo 0.16 | 2022-06-01
ipfs/kubo | Connect fails for /dnsaddr/.../wss but not /dns[4¦6]/../wss |  |  |  | 🥞 Todo | undefined | kind/bug, need/triage, P1 |  | undefined | undefined | undefined | kubo 0.16 | 2022-08-30
ipfs/kubo | [Tracking Issue] Cleanup Kubo RPC Client Story |  |  |  | 🥞 Todo | 2️⃣ P2 |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-07-26
ipfs/kubo | Create go-kubo-rpc-client library |  |  |  | 🥞 Todo | 2️⃣ P2 |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-07-19
ipfs/kubo | chore: update to go-log@v2 |  | Jorropo, guseggert |  | 🥞 Todo | undefined |  |  | blocked on issue to improve go-log side before moving forward here | undefined | undefined | kubo 0.16 | 2022-09-01
| ⬇️⬇️⬇️ Todo: Community / Process Items ⬇️⬇️⬇️ |  |  |  | 🥞 Todo | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-06-14
| ⬇️⬇️⬇️ Todo: Needs Sorting ⬇️⬇️⬇️ |  |  |  | 🥞 Todo | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-07-26
ipfs/kubo | Consider removing Snap |  |  |  | 🥞 Todo | undefined | P4, topic/docs-ipfs |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-15
| Ensure https://routing.delegate.ipfs.io/reframe has production support |  |  |  | 🥞 Todo | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-15
ipfs/ipfs-webui | Enabling WebTransport in Kubo v0.16.0-rc1 breaks Status page |  |  |  | 🥞 Todo | undefined | kind/bug, need/triage, P1, status/blocked |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-27
ipfs/ipfs-website | refactor: switch emails to @ipfs.tech |  |  |  | 🛑 Blocked | undefined | status/blocked |  | waiting for help@protocol.ai to set up GApps and DNS records | undefined | undefined | kubo 0.16 | 2022-07-27
| ⬇️⬇️⬇️ In Progress: Initiatives ⬇️⬇️⬇️ |  |  |  | 🏃‍♀️ In Progress | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-08-13
ipfs/kubo | Switch to go-log v2 |  |  | https://github.com/ipfs/kubo/pull/8765 | 🏃‍♀️ In Progress | undefined | kind/enhancement | Best Effort Track | undefined | ✔️ Yes | undefined | kubo 0.16 | 2022-03-24
ipfs/kubo | [Tracking issue] reframe used in production |  |  |  | 🏃‍♀️ In Progress | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-22
ipfs/kubo | Integrate/expose go-libp2p resource manager |  |  | https://github.com/ipfs/kubo/pull/8680 | 🏃‍♀️ In Progress | undefined | status/in-progress | kubo 0.15 | undefined | undefined | undefined | kubo 0.16 | 2022-09-27
ipfs/kubo | Move off CircleCI to GitHub Actions |  |  |  | 🏃‍♀️ In Progress | undefined | team/ipdx | TBD | undefined | undefined | undefined | kubo 0.16 | 2022-09-19
ipfs/kubo | Create js-kubo-rpc-client library |  |  |  | 🏃‍♀️ In Progress | 2️⃣ P2 | kind/maintenance |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-07
ipfs/kubo | Release 0.16 |  |  |  | 🏃‍♀️ In Progress | undefined | team/ipdx |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-30
| ⬇️⬇️⬇️ In Progress: Community / Process Items ⬇️⬇️⬇️ |  |  |  | 🏃‍♀️ In Progress | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-06-14
ipfs/specs | Update IPNS specification |  |  | https://github.com/ipfs/specs/pull/319 | 🏃‍♀️ In Progress | 1️⃣ P1 | dif/expert, P0 |  | undefined | ✔️ Yes | undefined | kubo 0.16 | 2022-09-06
ipfs/specs | feat: update IPNS specification |  | paulgmiller, aschmahmann, Winterhuman, vasco-santos, rvagg, Stebalien |  | 🏃‍♀️ In Progress | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-06
ipfs/kubo | Minimal rename of go-ipfs in 2022Q2 |  |  |  | 🏃‍♀️ In Progress | 1️⃣ P1 | effort/weeks, exp/expert, need/analysis, need/community-input, need/maintainers-input |  | undefined | undefined | undefined | kubo 0.16 | 2022-05-10
| ⬇️⬇️⬇️ In Progress: Items to Watch ⬇️⬇️⬇️ |  |  |  | 🏃‍♀️ In Progress | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-07-26
protocol/bifrost-infra | Move non-gateway services to *.ipfs.tech |  |  |  | 🏃‍♀️ In Progress | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-07-27
| ⬇️⬇️⬇️ In Progress: Needs Sorting ⬇️⬇️⬇️ |  |  |  | 🏃‍♀️ In Progress | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-08-13
ipfs/kubo | Handle any supported IPLD codec for CAR imports |  |  | https://github.com/ipfs/kubo/pull/9219 | 🏃‍♀️ In Progress | undefined | kind/enhancement, need/triage | Best Effort Track | undefined | ✔️ Yes | undefined | kubo 0.16 | 2022-08-19
libp2p/go-libp2p-kad-dht | Optimistic Provide |  | guseggert |  | 🏃‍♀️ In Progress | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-08
| Content routing decision doc |  |  |  | 🏃‍♀️ In Progress | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-22
ipfs/kubo | Improve sharness tests failure reports |  |  |  | 🏃‍♀️ In Progress | undefined | need/triage, team/ipdx, topic/ci |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-29
ipfs/kubo | 0.16.0-rc1: AcceleratedDHTClient possible issue? |  |  |  | 🏃‍♀️ In Progress | undefined | kind/bug, need/triage |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-30
| ⬇️⬇️⬇️ Review: Quick Win ⬇️⬇️⬇️ |  |  |  | 🔎 In Review | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-06-14
ipfs/fs-repo-migrations | plugins: add go mod tidy due to Go1.16 changes |  | guseggert, gammazero |  | 🔎 In Review | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-06-06
ipfs/specs | Update UnixFS specification |  |  |  | 🔎 In Review | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-15
| ⬇️⬇️⬇️ Review: Active Initiatives ⬇️⬇️⬇️ |  |  |  | 🔎 In Review | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-06-14
ipfs/kubo | feat: remove provider delay interval in bitswap |  | mrd0ll4r, yiannisbot, aschmahmann, Jorropo, guseggert |  | 🔎 In Review | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-07-25
| ⬇️⬇️⬇️ Review: Long Running Spec Items ⬇️⬇️⬇️ |  |  |  | 🔎 In Review | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-06-14
| ⬇️⬇️⬇️ Review: Unknown Priority ⬇️⬇️⬇️ |  |  |  | 🔎 In Review | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-06-14
ipfs/kubo | Optimizing (or remove) the provider delay interval for DHT lookups used by Bitswap |  |  | https://github.com/ipfs/kubo/pull/9053 | 🔎 In Review | undefined | kind/enhancement | kubo 0.15 | undefined | ✔️ Yes | undefined | kubo 0.16 | 2022-07-25
ipfs/go-ipfs-priv | ci: enable access to any private gh repo |  | Jorropo, BigLep |  | 🔎 In Review | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-03
ipfs/specs | feat: Content Routing Hints |  | willscott, aschmahmann, lidel |  | 🔎 In Review | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-20
ipfs/kubo | feat: --reset flag on swarm limit command |  | lidel, guseggert |  | 🔎 In Review | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-27
ipfs/kubo | Fix: `swarm stats all` command |  | Jorropo, guseggert |  | 🔎 In Review | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-28
ipfs/go-bitswap | Sending message > 4mb fails over libp2p |  | guseggert |  | 🔎 In Review | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-30
ipfs/go-bitswap | Separable client and server implementations | , |  |  | 🎉 Done | undefined | kind/enhancement |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-01
ipfs/go-unixfs | Fix race condition on childer. |  | schomatis, Jorropo, guseggert |  | 🎉 Done | undefined |  | Best Effort Track | Needs repo in https://github.com/ipfs/kubo/issues/9063 | undefined | undefined | kubo 0.16 | 2022-09-01
ipfs/kubo | Update RELEASE_ISSUE_TEMPLATE.md |  | BigLep, SgtPooki, lidel |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-19
ipfs/kubo | feat(cmds/add): --to-files option as files cp |  | lidel, Jorropo, ajnavarro |  | 🎉 Done | undefined |  |  | Blocked on ipfs/go-ipfs-files#53. | undefined | undefined | kubo 0.16 | 2022-09-21
ipfs/kubo | ipfs add --to-files=/path/in/mfs |  |  | https://github.com/ipfs/kubo/pull/8637, https://github.com/ipfs/kubo/pull/8927 | 🎉 Done | 2️⃣ P2 | exp/intermediate, kind/enhancement, need/triage, topic/api, topic/files | Best Effort Track | undefined | ✔️ Yes | undefined | kubo 0.16 | 2022-09-21
libp2p/go-libp2p-routing-helpers | New Routing helpers: `parallel` and `sequential`. |  |  | https://github.com/libp2p/go-libp2p-routing-helpers/pull/58 | 🎉 Done | undefined | effort/days, kind/enhancement |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-17
libp2p/go-libp2p-routing-helpers | feat: Sequential and Parallel Routers |  | guseggert |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-17
ipld/edelweiss | add cachable modifier to methods |  | guseggert |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-13
ipfs/kubo | feat(gateway): _redirects file support | , | lidel |  | 🎉 Done | undefined |  | Best Effort Track | @lidel needs to review both specs and Kubo PR | undefined | undefined | kubo 0.16 | 2022-09-23
ipfs/kubo | fix: require IPNS V2 signatures |  | ajnavarro, guseggert |  | 🎉 Done | 1️⃣ P1 |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-21
ipfs/ipfs-blog | [Blog Post] Introducing Reframe | , |  |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-03
ipfs/kubo | feat: Delegated routing with custom configuration. |  | guseggert |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-22
ipfs/kubo | Routing: conform DHT to common Router interface |  |  | https://github.com/ipfs/kubo/pull/9176, https://github.com/ipfs/kubo/pull/9274 | 🎉 Done | undefined | kind/feature |  | Needs design: https://github.com/ipfs/kubo/issues/9188 | ✔️ Yes | undefined | kubo 0.16 | 2022-09-22
ipfs/kubo | Routing: conform DHT to common Router interface |  |  |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-13
ipfs/go-delegated-routing | Add cacheable GET endpoint for findProviders |  |  |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-13
libp2p/hydra-booster | Update to use delegated-routing for querying storetheindex |  |  |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-15
ipfs/kubo | Update to go-libp2p 0.22 |  |  | https://github.com/ipfs/kubo/pull/9244 | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-09
ipfs/kubo | IPFS Option plugins |  |  | https://github.com/ipfs/kubo/pull/9010 | 🎉 Done | undefined | kind/feature, need/triage | Best Effort Track | undefined | ✔️ Yes | undefined | kubo 0.16 | 2022-08-13
ipfs/kubo | Remove support for deprecated IPNS records v1 |  |  | https://github.com/ipfs/kubo/pull/9265 | 🎉 Done | 1️⃣ P1 | dif/medium, effort/days, kind/maintenance, P1, topic/ipns |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-21
ipfs/kubo | chore: update go-pinning-service-http-client to include up to nano precision |  |  |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-01
ipfs/kubo | Should not return 416 for empty files when `Range` includes 0 |  |  | https://github.com/ipfs/kubo/pull/9241 | 🎉 Done | undefined | kind/bug, P2 |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-01
ipfs/kubo | fix(gw): send 200 for empty files |  | lidel |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-01
ipfs/go-cid | CodecToStr and Codecs in v0.3.1 could cause data corruption |  |  | https://github.com/ipfs/go-cid/pull/145 | 🎉 Done | undefined | kind/bug, need/triage, P0 |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-04
libp2p/hydra-booster-infra | Add periodic S3 export for DynamoDB tables |  | guseggert |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-14
ipfs/kubo | bump go-libp2p v0.22.0 & go1.18&go1.19 |  | lidel, ajnavarro |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-09
ipfs/kubo | Delegated Routing: Allow to configure methods used by router. |  |  | https://github.com/ipfs/kubo/pull/9274 | 🎉 Done | undefined | kind/feature |  | undefined | ✔️ Yes | undefined | kubo 0.16 | 2022-09-22
ipfs/go-bitswap | Bitswap v0.10.1 is causing the lotus sync tests to fail reliably |  |  | https://github.com/ipfs/go-bitswap/pull/585 | 🎉 Done | undefined | kind/bug |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-13
ipfs/kubo | chore: bump go-libp2p v0.23.1 |  | marten-seemann, lidel |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-22
ipfs/kubo | Support new libp2p WebTransport transport for experimentation |  |  | https://github.com/ipfs/kubo/pull/9293 | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-24
ipfs/kubo | `ipfs add` with exotic hash functions panics (the daemon and the client) |  |  | https://github.com/ipfs/kubo/pull/9303 | 🎉 Done | undefined | kind/bug, need/triage |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-26
ipfs/kubo | fix: ensure hasher is registered when using a hashing function |  | ajnavarro |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-26
ipfs/kubo | 0.16.0-rc1: `Routing.Methods` should be `null` |  |  | https://github.com/ipfs/kubo/pull/9313 | 🎉 Done | undefined | kind/bug, need/triage |  | undefined | ✔️ Yes | undefined | kubo 0.16 | 2022-09-27
ipfs/kubo | docs: document remaining 0.16.0 features |  | 2color, BigLep |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-09-29
ipfs/specs | fix: document GET /reframe?q= |  | BigLep, Jorropo, willscott, guseggert, petar |  | 🎉 Done | undefined |  |  | undefined | undefined | undefined | kubo 0.16 | 2022-10-01